## Sheet1
| 2017 | [9 empty] | 2018
Milestones | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | April
Publications | 2017 JUNE: Draft Smallholder Steering Committee TOR; 2017 JULY: Final Standard Steering Committee TOR (after review at first task force meeting); 2017 SEP: Draft of revised data collection; 2017 OCT: 1st Draft of Standard; 2017 DEC: 2nd Draft of standard; 2018 FEB: 3rd Draft of standard; 2018 April: Final publication
Meetings | 2017 MARCH: Bonsucro Board Approval; 2017 AUG: Smallholder Steering Committee Meeting (all interested); 2017 SEP: Standard Setting Task force meeting and Bonsucro Technical Advisory Board Meeting; 2017 OCT: Task force meeting; 2017 NOV: Task force meeting; 2017 DEC: Task force meeting; 2018 FEB: Task force meeting; 2018 MAR: Technical Advisory Board Meeting for request to approve standard
Consultations | 2017 JUNE: Mexico-consultation during Bonsucro Technical Week; 2017 JULY: Task Force- public communication, target list, one rep from each membership group; 2017 NOV: Consultation- webinars, in-person meetings where possible; 2018 FEB: Consultation- webinars, in-person meetings where possible, MC clusters
Pilots | 2017 MAY: Smallholder field visits in Thailand; 2017 JUNE: Smallholder field visits in Mexico; 2017 JULY: Smallholder field visit in India; 2018 JAN: Consultation- during Bonsucro Week; 2018 FEB: CB run pilot with Bonsucro oversight